## Slide 1
COUPA · SR. LEAD, P&T OPERATIONS · 90-DAY ROLLOUT
Turning the CuCP Framework into Adopted Reality
A 90-day plan to implement and scale the Customer Collaboration Program — from paper framework to predictable launch engine.
PRESENTED BY
Vittobha Vignesh S
ROLE
Sr. Lead, P&T Operations
PROGRAMME
Customer Collaboration (CuCP)
SCOPE
Days 1–90

## Slide 2
Change Management & Adoption Strategy
Change management starts with understanding the resistance, then flipping the narrative.
THE PROBLEM: FRAGMENTED EXECUTION
• Ad-hoc EAP/LA engagement, no standard process
• "Definition drift" — scope shifts before GA
• No exit criteria → risky launch decisions
• PMs see CuCP as admin overhead slowing velocity
STRATEGY: EARN ADOPTION, DON'T MANDATE IT
• Lead with PM pain — not programme goals
• Find proto-champions already doing EAP work
• Make first experience frictionless — I absorb the admin
• Their story converts sceptics, mine doesn't
The message that lands: "CuCP is your evidence kit — not a compliance checklist."
Structured EAP data protects PMs at GA. It answers "how do we know this is ready?" with customer signal, not gut feel.

## Slide 3
Capability Classifications: Standard vs. AI
Pre-GA validation strategies are structured to match the risk profile of each release path.
STANDARD CAPABILITIES
• Definition: Deterministic logic and workflows (no AI involved). E.g., dashboards, routing rules.
• Focus: Validate operational readiness, scalability, support enablement.
• Gating: Closed Beta (EAP) and Limited Availability (LA) require a $0 Order Form.
• Exit: LA phase gates readiness with commercial alignment before General Availability.
AI CAPABILITIES (AI-ASSISTED & AGENTIC)
• Definition: Powered by ML/LLMs. Probabilistic models. E.g., Copilots, Agent Studio.
• Focus: Model tuning, trust/safety guardrails, telemetry integration.
• Billing: EAP & Open Beta are free of charge via customer AI Credits.
• Gating: Open Beta is enabled via UI toggle (no $0 Order Forms; utilizes Fair Use Caps).
THE PRINCIPLE OF PROPORTIONAL GOVERNANCE
The level of release gating must align to feature risk, complexity, and operational impact. Pre-GA (LA & Open Beta) phases are optional and variable. The PM determines if Phase 2 is required based on features.

## Slide 4
90-Day Rollout Execution: Pilot → Learn → Scale
No big-bang mandate. Build trust through service, then scale on proven evidence.
PHASE 1
Days 1–30
Listen & Align
• 1:1 listening sessions (8–10 PMs)
• Shadow EAP/LA release cycles
• Map informal processes in use
• Identify proto-champions
• Select pilots: 1 Std + 1 AI release
Friction map + pilot cohort confirmed
PHASE 2
Days 31–60
Pilot & Refine
• Run 2–3 live CuCP pilots
• I act as embedded CuCP Concierge
• Weekly retros — cut admin overhead
• Capture before/after evidence
• Activate PM champions
Playbook v1.0 + champion stories
PHASE 3
Days 61–90
Scale & Institutionalise
• All-hands enablement session
• Self-serve KB + templates live
• #cucp-support + office hours
• Admin tasks automated
• Leadership dashboard live
All PMs enabled · tracking live

## Slide 5
Enablement & Support Model
Four pillars that make CuCP stupidly easy to run — before it becomes expected.
🎯 CuCP Concierge (Days 1–60)
I act as the operational support for pilot PMs. They learn the process; I handle templates, customer invites, and exit criteria tracking. PM overhead: near zero.
High-touch during pilot
📋 Playbook + Cheat Sheets
Two 1-page cheat sheets: Standard capability path and AI capability path. Separate because their pre-GA goals, cohort sizes, and exit criteria differ meaningfully.
Self-serve from Day 60
💬 #cucp-support + Office Hours
Live Slack channel for real-time questions. Weekly 30-min open office hours for the first 90 days. PMs get answers in minutes, not days — reduces perceived friction.
Async + sync support
🏆 Champion-Led Rollout
Pilot PMs present at the all-hands enablement session — not me. Peer stories are far more credible than top-down messaging for converting sceptics.
Peer credibility > authority

## Slide 6
Measuring Initial Success
Six metrics prove the rollout is working. One leading indicator matters most in the first 90 days.
KPI | BASELINE | DAY 90 TARGET | HOW MEASURED | TYPE
⭐ PM Satisfaction Score — "Is CuCP helping?" | — | ≥ 4.0 / 5.0 | Post-pilot survey | LEADING
% eligible releases using CuCP | 0% (ad-hoc) | ≥ 50% | Release tracker | LAGGING
EAP → GA cycle time | Measure Days 1–30 | No regression; –10% | Release logs | LAGGING
Definition drift incidents | Unmeasured | Tracked; 0 in pilots | EAP/LA retros | LEADING
Customer participation rate | — | ≥ 70% invited engage | CuCP tracker | LAGGING
PM admin time per release cycle | — | < 2 hours | PM self-report | LEADING
⭐ Key takeaway: If PMs feel CuCP helps — scaling is pull, not push. Fix the playbook before mandating.

## Slide 7
What Day 90 Looks Like
Three outcomes that prove the CuCP rollout succeeded — and what I need from leadership to get there.
EVIDENCE OF SUCCESS
✓ ≥ 50% eligible releases running CuCP
✓ PM satisfaction score ≥ 4.0 / 5.0
✓ 2–3 champion PMs advocating internally
✓ Self-serve KB live — zero dependency on me
PROPORTIONAL GOVERNANCE PRINCIPLE
✓ Days 1–30: Observe only, map release landscape
✓ Days 31–60: Voluntary pilot, embedding Concierge
✓ Days 61–90: Clear expectation for eligible cohorts
✓ Day 90+: Data-backed mandate, confirmed by feedback
MY ASK OF P&T LEADERSHIP
🛡️ Air cover during pilot — no forced mandate
🎙️ Exec sponsor for all-hands session
🔗 Access to 2–3 willing pilot PMs in Week 1
📊 Release log access for baseline measurement